NAO publish Apprenticeships Report "Delivering value through the apprenticeship programme".

https://www.nao.org.uk/report/delivery-value-through-the-apprenticeships-programme/

The NAO raise concerns regarding apprenticeship reforms and the opportunities for financial abuse - especially pertinent in the light of AELP information that some employers are attempting to "charge" providers for access to their levy funds.

The key findings include that the DfE should:

1. Set out the planned overall impact on productivity and growth, along with short term key performance indicators to measure the apprenticeship programme's success.

2. Ensure that the timescale for further development of Trailblazer standards remains realistic, and is well communicated to employers and providers.

3. Improves the way it handles key risks, interdependencies and contingencies across the various elements of the programme.

4. Do more to understand how employers, training providers and assessment bodies may respond to ongoing reforms, and develop robust ways of reacting quickly should instances of market abuse emerge.
5. Determine the respective roles of government bodies and the Institute for Apprenticeships, with particular regard to: overseeing the quality of apprenticeship training; and collecting and analysing relevant data and metrics